## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Viswas | 2026-10-14 | Python syntax errors not identified during initial code validation. | Sprint 1 | Viswas | Standards | Improve Python syntax validation and error handling. | 2026-10-14 | Closed | Requires testing
2 | Viswas | 2026-10-15 | Gemini model flash 3.7 not working | Sprint 1 | Viswas | Standards | Changed the Google Api model | 2026-10-15 | Closed | Problem with offical Google Model

## Sheet2
Logical
User Interface
Maintainability
Standards
Others